## Sheet1
Item | Description | Points | Score | Specific Questions or Comments on Items
1 | Bid Proposal | 20 | 0
| Completeness of proposal | 10 |  | ALL DELIVERABLES WITH BID.
| Variance between Contractor's Bid compared to Sponsor's Baseline Bid | 10 |  | < 5% = 10: 5% to 10% = 9: 10% to 20% = 8: 20% to 30% = 7: 40% to 50% = 6: 60% to 70% = 5: 70% to 80% = 4: 80% to 90% = 2: > 90% = 0
2 | Estimate | 40 | 0
| Quantity takeoff (accuracy & completeness) for Bid Items Required in List of Deliverables | 30 |  | Show weights, volumes, and piece quantity for all permanent materials.
| Direct cost pricing (labor & equipment) | 5
| Direct cost pricing (material & subcontractor) | 5
3 | Construction Schedule | 8 | 0
| Completeness | 5
| Logic analysis | 3
4 | Means & Methods | 30 | 0
| Understanding of specification requirements | 5
| Mobilization and Access | 5
| Precast Concrete Erection (including step by step written procedure) | 5
| Cast in Place Concrete (including step by step written procedure) | 5
| Proper utilization of labor & equipment | 5
| Efficiency/Creativity of approach | 5
5 | Project Overhead | 7 | 0
| Organization chart | 4
| Overhead cost calculations | 3
6 | Questions | 10 | 0
| Quality of RFI questions asked | 5
| Quality of Subcontractor / Vendor questions asked | 5
7 | Oral Presentation - Bid Review | 35 | 0
| Participation by Every Team Member | 10
| Safety | 5 |  | Be specific as to the hazards that relate to this project.
| Schedule | 5
| Equipment selection | 5
| Means and methods | 5
| Answers to questions | 5
| Total Score | 150 | 0
General Questions or Comments
Late Proposals: 1 second to 5 minutes late -15 pts., greater than 5 minutes late -25 pts. Note: In real life your proposal would not be excepted late.